## Action Log
2024/2025 Llais Board Action Items Tracker Traciwr Eitemau Gweithredu Bwrdd Llais 2024/2025
Cyfeirnod y Gweithred / Action Reference | Nodau ac Eitemau Gweithredu / Goals & Action Items | Rhanbarth Cyfrifol / Region Responsible | Person/Pobl Cyfrifol / Person(s) Responsible | Dyddiad Dechrau / Start Date | Dyddiad Dyledus / Due Date | Statws / Status | % cwblhad pob eitem weithredu / % completion of each action item | Diweddariad / Nodiadau - Update / Notes | Materion / Issues | Datrysiad i'r Mater / Issue Resolution | Dyddiad Datrysiad i'r Mater / Resolution Date
A24-07-01 | Report from Chair: Chief Executive to submit a response to the Welsh Government consultation on Partnership working to confirm Llais's intention to engage with partners to highlight significant issues in health and social care and seek integrated approaches. WELSH: Y Prif Weithredwr i gyflwyno ymateb i ymgynghoriad Llywodraeth Cymru ar weithio mewn Partneriaeth i gadarnhau bwriad Llais i ymgysylltu â phartneriaid i amlygu materion sylweddol ym maes iechyd a gofal cymdeithasol a cheisio dulliau integredig. | National Team | Alyson Thomas | 2024-07-01 | 2024-09-01 | In Progress | 75% | Response developed and update will be provided at the meeting. WELSH: Ymateb wedi'i ddatblygu a bydd diweddariad yn cael ei ddarparu yn y cyfarfod.
A24-07-02 | Standing Orders: It was agreed that the standing orders would be posted to the Llais website and that awareness raising with staff would be undertaken to develop understanding and compliance. WELSH: Cytunwyd y byddai'r rheolau sefydlog yn cael eu cyhoeddi ar wefan Llais ac y byddai'r staff yn codi ymwybyddiaeth er mwyn datblygu dealltwriaeth a chydymffurfiaeth. | Governance | Richard Bevan | 2024-07-01 | 2024-09-01 | In Progress | 75% | New Governance pages have been developed on the intranet and all Governance documentation will be available on these pages. The Interim Board Secretary has raised awareness with Tim Arwain and offered development sessions for regions and functions. WELSH: Mae tudalennau Llywodraethu newydd wedi'u datblygu ar y fewnrwyd a bydd yr holl ddogfennau Llywodraethu ar gael ar y tudalennau hyn. Mae Ysgrifennydd Dros Dro'r Bwrdd wedi codi ymwybyddiaeth gyda Tim Arwain ac wedi cynnig sesiynau datblygu ar gyfer rhanbarthau a swyddogaethau.
A24-07-03 | Board Schedule: It was agreed that the schedule of matters reserved would be posted to the Llais website. WELSH: Cytunwyd y byddai'r rhestr o faterion a gadwyd yn ôl yn cael ei chyhoeddi i wefan Llais. | Governance | Richard Bevan | 2024-07-01 | 2024-09-01 | In Progress | 75% | New Governance pages have been developed on the intranet and all Governance documentation will be available on these pages. The Interim Board Secretary has raised awareness with Tim Arwain and offered development sessions for regions and functions. WELSH: Mae tudalennau Llywodraethu newydd wedi'u datblygu ar y fewnrwyd a bydd yr holl ddogfennau Llywodraethu ar gael ar y tudalennau hyn. Mae Ysgrifennydd Dros Dro'r Bwrdd wedi codi ymwybyddiaeth gyda Tim Arwain ac wedi cynnig sesiynau datblygu ar gyfer rhanbarthau a swyddogaethau.
A24-04-02 | Public Statement: The Chief Executive, as part of the communications arrangements for Llais, would publish a regular statement for the public to highlight the work of Llais and its key achievements and impacts. WELSH: Byddai'r Prif Weithredwr, fel rhan o drefniadau cyfathrebu Llais, yn cyhoeddi datganiad rheolaidd i'r cyhoedd i dynnu sylw at waith Llais a'i gyflawniadau a'i effeithiau allweddol. | National Team | Alyson Thomas | 2024-04-01 | 2024-07-01 | In Progress | 75% | The first public statement is due to be published in October 2024 WELSH: Disgwylir i’r datganiad cyhoeddus cyntaf gael ei gyhoeddi ym mis Hydref 2024
A24-04-03 | Corporate Risk: The Board agreed that a new dashboard style Corporate Risk Report/Register would be developed and presented at the July 2024 Board. WELSH: Cytunodd y Bwrdd y byddai Adroddiad/Cofrestr Risg Corfforaethol ar ffurf dangosfwrdd yn cael ei datblygu a’i chyflwyno i’r Bwrdd ym mis Gorffennaf 2024. | Governance | Richard Bevan | 2024-04-01 | 2024-07-01 | Complete | 100% | An interim dashboard was presented at the July Board and further work is underway to develop a finalised dashboard linked to the OKR system. WELSH: Cyflwynwyd dangosfwrdd interim i'r Bwrdd ym mis Gorffennaf ac mae gwaith pellach ar y gweill i ddatblygu dangosfwrdd terfynol sy'n gysylltiedig â'r system OKR.
A24-01-02 | Workforce Metrics: The National Team to provide further information on the diversity of applicants applying for roles within Llais. WELSH: Y Tîm Cenedlaethol i ddarparu rhagor o wybodaeth am amrywiaeth yr ymgeiswyr sy'n ymgeisio am rolau o fewn Llais. | National Team | Joanne Bolton/Chris Davies | 2024-01-01 | 2024-07-01 | In Progress | 75% | Workforce metrics will be included in reports to the Workforce, Remuneration and Terms of Service Committee and high-level workforce dashboard reports to the Board. A new worksforce dashboard will be presented to the September board. WELSH: Bydd metrigau gweithlu'n cael eu cynnwys mewn adroddiadau i'r Pwyllgor Gweithlu, Tâl a Thelerau Gwasanaeth ac adroddiadau dangosfwrdd gweithlu lefel uchel i'r Bwrdd. Bydd dangosfwrdd gweithlu newydd yn cael ei gyflwyno i fwrdd mis Medi.

## Closed Actions
2024/2025 Llais Board Closed Actions Tracker
Action Reference | Action Items | Region Responsible | Person(s) Responsible | Start Date | Due Date | Status | % completion of each action item | Notes | Issues | Issue Resolution | Issue Resolution Date
A23-05-06 | Produce summary and easy read version of the ‘Our first 100 days’ report for publication. WELSH: |  | Ben Eaton | 2023-05-01 | 2024-01-01 | Complete | 100%
A23-05-02 | The Board noted the expected timeline with the establishment of the Llais IT systems and asked that this was kept under review. WELSH: |  | Angela Mutlow | 2023-05-01 | 2024-01-01 | Complete | 100%
A23-03-13 | Head of IT and Infrastructure to review security policy within the first 3 months of operations. WELSH: |  | Head of IT&I | 2024-03-01 | 2024-03-01 | Complete | 100%
A23-01-11 | Amend section related to complaints about CHCs from the complaint’s procedure in April 2024. WELSH: |  | Governance | 2024-01-01 | 2024-04-01 | Complete | 100%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%
[6 empty] | Not Started | 0%

## Decisions
2024/2025 Llais Board Decisions Tracker
Decision Reference | Action Items | Region Responsible | Person(s) Responsible | Start Date | Due Date | Notes | Issues | Issue Resolution | Issue Resolution Date | Overall RAG Status
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started